## Plan
TPO Platform - Enhancement Roadmap
Retail Intelligence Platform ¦ Trade Promotion Optimisation
ID | Workstream | Task | Scope | Start | End | Team member | Owner | Status | Depends on | Deliverable | Notes
1 | Insights Hub | Insights Hub workstream |  | 2026-09-16 | 2026-09-25
1.1 | Insights Hub | Research: user-configurable KPI cards | Survey candidate KPIs, define the add/remove card model and persistence; produce a shortlist with a recommendation. | 2026-09-16 | 2026-09-16 | Shiva | Sajan | Not started |  | KPI options note with recommended set
1.2 | Insights Hub | TPO-specific Insights Hub enhancements | Implement the Insights Hub changes agreed for trade promotion optimisation (layout, cards, filters). | 2026-09-17 | 2026-09-18 | Shiva | Swarnim | Not started | 1.1 | Updated Insights Hub in dev
1.3 | Insights Hub | Dynamic ROI implementation | ROI recalculates live against the selected scope and period, consistent with the Incremental Sales / Trade Spend multiple used across the platform. | 2026-09-21 | 2026-09-22 | Swarnim | Sajan | Not started | 1.2 | Dynamic ROI on all Insights Hub cards
1.4 | Insights Hub | Insights Hub conversational assistant | Chat interface that answers questions over the current Insights Hub view and explains the figures shown. | 2026-09-23 | 2026-09-25 | Swarnim | Sajan | Not started | 1.3 | Assistant panel wired to Insights Hub data
2 | Investigations | Investigations workstream |  | 2026-09-28 | 2026-09-30
2.1 | Investigations | Feature and UX enhancements | Workflow, filtering and presentation improvements to the Investigations workspace. | 2026-09-28 | 2026-09-29 | Shiva | Swarnim | Not started |  | Updated Investigations module
2.2 | Investigations | Alignment, navigation and change review | Align Investigations with Insights Hub conventions, tidy navigation, and review all changes delivered so far. | 2026-09-30 | 2026-09-30 | Swarnim | Sajan | Not started | 2.1 | Review sign-off; defect list
3 | Promotion Intelligence | Promotion Intelligence workstream |  | 2026-10-01 | 2026-10-06
3.1 | Promotion Intelligence | UI refinements | Visual and interaction updates to bring Promotion Intelligence in line with the refreshed modules. | 2026-10-01 | 2026-10-01 | Shiva | Sajan | Not started | 2.2 | Updated Promotion Intelligence UI
3.2 | Promotion Intelligence | Feature enhancements | New analytical capabilities and data views for promotion performance. | 2026-10-05 | 2026-10-06 | Swarnim | Sajan | Not started | 3.1 | Feature set released to dev
4 | Simulation Studio | Simulation Studio workstream |  | 2026-10-07 | 2026-10-13
4.1 | Simulation Studio | Executive visualisations: trade spend, ROI and profit | High-level charts and plan-versus-outcome insights covering trade spend, ROI and profit for simulated scenarios. | 2026-10-07 | 2026-10-13 | Swarnim | Sajan | Not started | 3.2 | Simulation Studio summary views
5 | Decision Center | Decision Center workstream |  | 2026-10-14 | 2026-10-16
5.1 | Decision Center | Decision Center enhancements | Consolidate outputs from the other modules into decision-ready recommendations and actions. | 2026-10-14 | 2026-10-16 | Shiva | Sajan | Not started | 4.1 | Updated Decision Center